Strengthening the Childcare Workforce in Refugee Communities

Building a Professionalized, Community-Financed Childcare Economy in Refugee-Hosting Contexts

# 1. Executive Summary

Uganda hosts one of the largest refugee populations in Africa, and children aged 0 to 5 remain the least served group in its settlements. In Nakivale Refugee Settlement, childcare is provided almost entirely through informal, unpaid arrangements carried by refugee women, with limited training, recognition or income. Uganda's new Early Childhood Care and Education (ECCE) Policy has opened a rare window to change this.

Kupanda Collective proposes a three-year, USD 800,000 initiative that treats childcare in Nakivale Refugee Settlement as an economy to be built through a professionalized workforce holding nationally recognized credentials, a network of refugee-led childcare enterprises with their own revenue and capital, services registered within government systems, and evidence rigorous enough to price national scale-up. The initiative concentrates on Nakivale as a single, deeply implemented demonstration site, and builds the costed model, evidence and delivery kit needed for replication across refugee-hosting districts in a subsequent phase.

Over three years, the initiative will certify 300 caregivers through a Childcare Caregivers Incubator linked to the Directorate of Industrial Training (DIT); capitalize a cooperative-owned Childcare Enterprise Fund financing 120 refugee-led childcare enterprises; reach 8,000 children aged 0 to 5 with safe, nurturing, play-based care; register 80 services with Local Government and the Education Management Information System (EMIS); and produce a rigorous costed evidence base for childcare in protracted displacement, including a published reference cost per child. By Year 3, fee and community revenue is projected to cover 30% of enterprise operating costs, with district engagement laying the ground for public co-financing beyond the grant.

# 2. About Kupanda Collective

Kupanda is a Swahili word meaning growth. Kupanda Collective is a Uganda-based, women-led non-government organization advancing inclusive, community-led development for refugee and host communities, with a focus on early childhood development, caregiver empowerment, health integration and social cohesion. Kupanda Collective operates on the principle that communities already possess trusted structures and leadership that, when strengthened and connected, deliver sustainable outcomes for children and families.

Our vision is that refugee and host communities thrive through integrated, community-led systems that support child development, economic participation and long-term self-reliance. Our mission is to strengthen the community-led systems that make this possible. Over the past two years, Kupanda Collective has worked with refugee caregivers, host community members, refugee-led organizations, local leaders and government actors, and building the trust and legitimacy needed to design solutions with communities. Our strategic interventions of Neighborhood Assemblies, community-led People's Parliaments for dialogue, priority setting and social accountability, anchor this work.

# 3. Context and the Policy Window

Most refugees in Uganda live in long-established settlements where displacement is protracted. Humanitarian responses have historically prioritized food assistance, health, water and primary education, leaving childcare for children aged 0 to 5 under-prioritized. Existing childcare spaces are few, unevenly distributed and largely informal. This gap undermines young children's development and places a disproportionate burden on women, whose participation in livelihoods, training and community life depends on whether safe, reliable childcare exists nearby.

Settlements such as Nakivale also hold significant untapped caregiving capacity. Refugee women are already caring for children through trusted community arrangements. Strengthened, credentialed and financed, this capacity can become a professional workforce and a source of dignified income.

The Early Childhood Care and Education Policy commits to expanding access, strengthening the ECCE workforce, supporting registration and licensing, improving coordination and generating better data. The candid question is how these reforms will reach refugee children, informal providers and the women carrying unpaid care work in settlements. This initiative is designed to answer that question in practice and to hand government a tested, costed model for doing so.

# 4. The Initiative: A Childcare Economy Model

Strengthening the Childcare Workforce in Refugee Communities invests in the childcare workforce as the foundation for nurturing care, women's economic participation and refugee self-reliance. For childcare in displacement settings to survive beyond any childcare in refugee communities to last, it must become part of everyday community and economic life. Caregivers also need recognized qualifications that remain useful wherever life takes them. Services earn revenue from the communities they serve. Enterprises access capital to start and grow. Government systems recognize, register and gradually co-finance what works. Evidence prices the model for scale. Each pillar of the programme builds one of these features, and together they form an engine that continues running after external funding ends.

## 4.1 Goal

To improve nurturing care and early childhood development outcomes for young refugee and host community children while expanding women's economic participation, through a professionalized, credentialed, refugee-led childcare economy embedded in community governance and national ECCE systems.

## Objectives

- Expand access to equitable, safe, inclusive, quality childcare for 8,000 children aged 0 to 5 in Nakivale Refugee Settlement.

- Build a credentialed childcare workforce of 300 caregivers, with refugee women recognized through nationally portable DIT-assessed qualifications.

- Establish a self-strengthening childcare market: 120 refugee-led childcare enterprises supported by a cooperative-owned Enterprise Fund and growing fee revenue.

- Integrate refugee-led childcare into settlement governance and national ECCE systems, including registration, licensing pathways, EMIS capture, quality assurance and district co-financing.

- Generate the evidence base for scale, anchored in a published reference cost per child for settlement childcare and a replication kit that refugee-led organizations can deliver.

# 5. Project Design

## 5.1 The Childcare Caregivers Incubator and a Credential that Travels

The Incubator trains refugee women and youth already providing childcare in responsive caregiving, play-based early learning, child protection and safeguarding, inclusion of children with disabilities, the Nurturing Care Framework, and foundational enterprise skills including record keeping and service organization. Delivery combines practical sessions, peer learning and on-site coaching.

What distinguishes the Incubator is its endpoint. Kupanda Collective will partner with the Directorate of Industrial Training so that graduates sit for formal assessment under the Workers' Practically Acquired Skills framework, earning a nationally recognized credential in early childhood caregiving. The credential converts training into a profession. It makes caregivers employable inside and beyond the settlement, gives government a workforce it can count and plan for under the ECCE Policy's workforce pillar, and gives refugee women a qualification that remains theirs wherever they go, including upon return or resettlement.

## 5.2 The Childcare Enterprise Fund

The initiative builds both sides of a childcare market. On the supply side, a cooperative-owned Childcare Enterprise Fund provides start-up and growth capital to certified caregivers establishing centres, home-based services and mobile childcare. Caregivers join savings groups, cooperatives and livelihood associations that strengthen income stability and collective bargaining, and that will progressively own and govern the Fund itself.

On the demand side, the initiative links childcare to the income already flowing through settlement economies. Market-day childcare will be co-financed by vendor associations at MATIF and similar market sites. Fee support will be tied to women's enterprise groups under the World Bank-funded GROW Project, whose participants need reliable childcare to work. Matched savings products within village savings and loan associations will help households budget for care. As caregiver incomes rise across the settlement economy, willingness and ability to pay modest fees rises with them, and each strand reinforces the other.

Cost per child is projected to fall from roughly USD 120 in Year 1 to roughly USD 80 by Year 3 as enrolment grows and fee revenue expands, with community revenue covering 30% of enterprise operating costs by close of grant. These figures will be validated through the baseline cost study and revised transparently.

## 5.3 Quality, Safety and Integrated Nurturing Care

Childcare centres, home-based arrangements and community spaces will operate as integrated nurturing care platforms: safe and stimulating environments, developmentally appropriate play and learning, embedded health and nutrition promotion, and strengthened referral pathways for child protection, health and social services. Quality assurance tools and supportive supervision will be introduced jointly with District Local Government, aligned with national ECCE standards, so that quality improvement and government oversight develop as a single system.

## 5.4 Community Participation and Social Accountability

Neighborhood Assemblies remain the governance spine of the initiative. Refugee caregivers, parents and community leaders will use these structured platforms to co-design services, set priorities, monitor quality, resolve grievances and engage duty bearers. Assemblies will also govern community rules for the Enterprise Fund and fee arrangements, keeping affordability and inclusion under community control. Insights from the Assemblies will feed directly into district and national advocacy for childcare investment.

## 5.5 Systems Integration and Government Co-Ownership

From the outset, the initiative will be implemented with the Office of the Prime Minister, the Ministry of Education and Sports, the Ministry of Gneder, Labour and Social Development, District Local Governments and settlement leadership as co-owners. Concrete commitments will include registration and licensing pathways for refugee-led services, EMIS capture of supported centres, adaptation of ECCE quality standards to settlement realities, and settlement ECCE implementation guidelines developed for adoption across refugee-hosting districts. The initiative will pursue district co-financing commitments within the grant period.

## 5.6 Evidence, Learning and the Cost Benchmark

Credible cost and outcome data for childcare in protracted displacement remain scarce. At this scale, the initiative will commission a focused costing and outcomes study with an independent research partner, with baseline and endline measurement of child development outcomes, women's income and labour participation, service quality and unit costs, culminating in a published reference cost per child for settlement childcare. Alongside the study, a test-and-learn approach will document implementation in real time, and the model will be packaged as a replication kit that refugee-led organizations can run with light support. Together, the reference cost and the kit give government and funders what they need to appraise and budget a larger second phase.

# 6. Phasing and Scale Architecture

| Phase | Focus |
| --- | --- |
| Year 1 | Foundation phase. Establish the Childcare Caregivers Incubator; conclude the DIT credentialing partnership; map existing caregivers and services; complete the baseline and costing study; design the Childcare Enterprise Fund with cooperatives and Neighborhood Assemblies; agree registration pathways with OPM, MoES and Isingiro District Local Government. |
| Year 2 | Scale phase. First cohorts certified; Enterprise Fund capitalized and first childcare enterprises financed; demand-side financing piloted around GROW and MATIF market sites; quality assurance and supportive supervision operating with Local Government; first services registered and entered in EMIS. |
| Year 3 | Consolidation and replication readiness. Final cohorts certified; fee revenue targets reached; endline and costing study published; replication kit finalized and refugee-led organizations oriented for second-phase delivery; settlement ECCE implementation guidance shared with district and national actors; dissemination with government, Hilton Foundation partners and the ECD community of practice. |

# 7. Results Framework

Indicators will be disaggregated by sex, refugee and host status, and disability.

| Result area | Indicator | Three-year target |
| --- | --- | --- |
| Access to quality childcare | Children aged 0 to 5 attending supported childcare services in Nakivale | 8,000 |
| Professionalized workforce | Caregivers completing the Incubator and attaining a nationally recognized DIT-assessed credential (at least 60% refugee women) | 300 |
| Childcare enterprises | Refugee-led childcare enterprises (centres, home-based and mobile services) operating to agreed quality standards | 120 |
| Financial sustainability | Share of enterprise operating costs covered by fee and community revenue by Year 3 | 30% |
| Caregiver livelihoods | Average increase in monthly income of certified caregivers against baseline | +50% |
| Systems integration | Childcare services registered with Local Government and captured in EMIS | 80 |
| Government adoption | Districts adopting settlement ECCE implementation guidance informed by the model | 1 |
| Evidence for scale | Published costing and outcomes study and replication kit, with refugee-led organizations oriented for second-phase delivery | 1 study; 3 RLOs |

# 8. Three – Year Budget by Project Component

| Budget category | Year 1 | Year 2 | Year 3 | Total (USD) | Share |
| --- | --- | --- | --- | --- | --- |
| Childcare workforce development and credentialing | 70,000 | 65,000 | 45,000 | 180,000 | 22.5% |
| Childcare Access Window | 20,000 | 45,000 | 35,000 | 100,000 | 12.5% |
| Childcare Enterprise Window and service quality | 35,000 | 55,000 | 35,000 | 125,000 | 15.6% |
| Integrated nurturing care and inclusion | 25,000 | 25,000 | 20,000 | 70,000 | 8.8% |
| Systems integration and the CAREWORKS Compact | 20,000 | 15,000 | 10,000 | 45,000 | 5.6% |
| Community governance and advocacy | 10,000 | 10,000 | 10,000 | 30,000 | 3.8% |
| Monitoring, evaluation, costing and learning | 30,000 | 15,000 | 25,000 | 70,000 | 8.8% |
| Project Personnel, Administration and Operations | 51,000 | 52,000 | 52,000 | 155,000 | 19.4% |
| Audit, safeguarding and institutional compliance | 8,000 | 8,000 | 9,000 | 25,000 | 3.1% |
| TOTAL | 269,000 | 290,000 | 241,000 | 800,000 | 100% |

# 9. Why Kupanda Collective, Why Now

Uganda is moving into the ECCE policy implementation, and decisions taken in the next three years will determine whether refugee children and informal providers are inside or outside that process. Kupanda Collective brings the deep, trust-based presence in Nakivale built through two years of community-led work, and working relationships across settlement leadership, refugee-led organizations, District Local Government and national ECCE actors. Childcare in refugee settings is deeply relational. Families trust people they know, and models designed together with communities hold. Kupanda Collective's Neighborhood Assemblies make that co-design real.

For the Hilton Foundation, the initiative offers a distinctive proposition: a single investment that professionalizes a refugee workforce, builds a community-financed care market, operationalizes a national policy in displacement settings, and produces costed evidence the field currently lacks.

# 11. Conclusion

Refugee children deserve to be visible in Uganda's ECCE implementation journey, and refugee women deserve recognition as the workforce that will make that vision real. With a USD 800,000 partnership, Nakivale becomes the demonstration site for a childcare economy in displacement: credentialed by government, financed increasingly by its own community, governed by the people it serves, and measured well enough to be priced for national scale. Kupanda Collective invites the Hilton Foundation to build it together.